## Project
Field | Value
Project name | Demo: Greenfield Substation
EPEC project code | DEMO
EPEC project number | 0999
Client | Example Renewables Pty Ltd
Client project name | Greenfield Solar Farm
Client project number
Client project code | GSF
Client PO number | PO-000123
Client project manager | Sam Client
EPEC project manager | Alex Marsden
Contract reference | EXAMPLE-EPC-2025-001
Early works reference | EXAMPLE-EW-2025-001
Status date (YYYY-MM-DD) | 2026-09-30
Project start | 2025-02-03
Project end | 2026-11-30
Grid start (first month shown) | 2025-01-01
Grid end (last month shown) | 2027-01-31
Default risk % of budget (e.g. 0.07) | 0.07

## CBS & Allowance
Parent code | Type | Group path | Name | Resource code | Resource name | Function / trade | Budget | Risk (blank = project default) | Method | Start | End | PO no | Notes
PL01 | Group |  | Project Manager |  |  |  | 330000
PL01 | Group |  | Project Coordinator |  |  |  | 190000
PL01 | Group |  | Contract Manager |  |  |  | 120000
PL01 | Group |  | HSEQ |  |  |  | 150000
PL02 | Group |  | Design Manager |  |  |  | 120000
PL02 | Group |  | Senior Designer |  |  |  | 210000
PL02 | Group |  | Substation Design Engineer |  |  |  | 180000
PL02 | Group |  | Drafting |  |  |  | 90000
PL03 | Group |  | Principal Engineer |  |  |  | 160000
PL03 | Group |  | Project Engineer |  |  |  | 140000
PL04 | Group |  | Construction Manager |  |  |  | 300000
PL04 | Group |  | Site Supervision |  |  |  | 360000
PL04 | Group |  | Site Admin |  |  |  | 90000
PL05 | Group |  | Commissioning |  |  |  | 330000
PL07 | Group |  | SCADA Engineering |  |  |  | 110000
PS02 | Group |  | Detailed design |  |  |  | 420000
PS04 | Group |  | Civil works |  |  |  | 1650000
PS04 | Group |  | Electrical installation |  |  |  | 1250000
PS05 | Group |  | Independent testing |  |  |  | 180000
PS07 | Group |  | SCADA integration |  |  |  | 360000
PM02 | Group |  | Power transformers |  |  |  | 1450000
PM03 | Group |  | 33kV and 132kV switchgear |  |  |  | 1380000
PM04 | Group |  | Protection and control |  |  |  | 520000
PM05 | Group |  | Power and control cables |  |  |  | 430000
PM06 | Group |  | Miscellaneous materials |  |  |  | 120000
PM07 | Group |  | Concrete, steel and civil materials |  |  |  | 520000
PE01 | Group |  | Travel and accommodation |  |  |  | 230000
PE02 | Group |  | Plant hire |  |  |  | 260000
PE03 | Group |  | Site indirects |  |  |  | 180000
PE05 | Group |  | Freight |  |  |  | 160000
PE07 | Group |  | Insurance |  |  |  | 70000
PL01 | Line |  | Alex Marsden | PM01 | Alex Marsden | Senior Project Manager | 0
PL01 | Line |  | Blair Okafor | PC01 | Blair Okafor | Project Coordinator | 0
PL01 | Line |  | Casey Lindqvist | CM01 | Casey Lindqvist | Contract Manager | 0
PL01 | Line |  | Dana Whitfield | HS01 | Dana Whitfield | HSEQ Adviser | 0
PL02 | Line |  | Eden Castellano | DM01 | Eden Castellano | Design Manager | 0
PL02 | Line |  | Frankie Nowak | SD01 | Frankie Nowak | Senior Designer | 0
PL02 | Line |  | Gale Thornton | D101 | Gale Thornton | Substation Design Engineer | 0
PL02 | Line |  | Harper Quinn | D201 | Harper Quinn | Engineer Designer | 0
PL03 | Line |  | Indy Rasmussen | EN01 | Indy Rasmussen | Principal Engineer | 0
PL03 | Line |  | Jules Abernathy | E201 | Jules Abernathy | Project Engineer | 0
PL04 | Line |  | Kai Brennan | CO01 | Kai Brennan | Construction Manager | 0
PL04 | Line |  | Lane Moreau | SS01 | Lane Moreau | Site Supervisor Electrical | 0
PL04 | Line |  | Morgan Delacroix | SC01 | Morgan Delacroix | Site Supervisor Civil | 0
PL04 | Line |  | Nico Valdez | SA01 | Nico Valdez | Site Admin | 0
PL05 | Line |  | Oakley Baird | TC01 | Oakley Baird | Commissioning Engineer | 0
PL05 | Line |  | Parker Linden | TM01 | Parker Linden | Commissioning Manager | 0
PL07 | Line |  | Quinn Ashworth | SE01 | Quinn Ashworth | SCADA Engineer | 0
PS04 | Line |  | Northbridge Civil Pty Ltd | S30NBC01 | Northbridge Civil Pty Ltd | Civil Contractor | 0
PS04 | Line |  | Larkspur Electrical Pty Ltd | S30LEC01 | Larkspur Electrical Pty Ltd | Electrical Contractor | 0
PS02 | Line |  | Arden Consulting Engineers | S30ARC01 | Arden Consulting Engineers | Design Consultancy | 0
PS05 | Line |  | Tallowood Testing Services | S30TST01 | Tallowood Testing Services | Testing | 0
PS07 | Line |  | Meridian SCADA Systems | S30SCD01 | Meridian SCADA Systems | SCADA | 0
PM02 | Line |  | Corvus Transformers Pty Ltd | S30TRX01 | Corvus Transformers Pty Ltd | Transformers | 0
PM03 | Line |  | Halden Switchgear | S30SWG01 | Halden Switchgear | Primary Equipment | 0
PM04 | Line |  | Quillon Protection | S30PRT01 | Quillon Protection | Relays | 0
PM05 | Line |  | Brightwater Cables | S30CAB01 | Brightwater Cables | Cables | 0
PM07 | Line |  | Redgum Concrete and Steel | S30CIV01 | Redgum Concrete and Steel | Civil Materials | 0
PE02 | Line |  | Westfield Plant Hire | S30HIR01 | Westfield Plant Hire | Equipment hire | 0
PE01 | Line |  | Lakeside Motel | S30ACC01 | Lakeside Motel | Accommodation | 0
PE05 | Line |  | Overland Freight | S30FRT01 | Overland Freight | Freight | 0

## Payment Milestones
Ref | Description | Stage | Kind | Value | Phase | Start | End | Method | Claim requirement | Optional status
1.01 | Preliminaries | EPC | base | 2101000 | Mobilisation | 2025-02-01 | 2026-11-30 | even | Monthly in arrears
1.02 | Design | EPC | base | 1436000 | Design | 2025-02-01 | 2025-11-30 | even | Design milestones
1.03 | Primary plant supply | EPC | base | 4456000 | Procurement | 2025-05-01 | 2026-03-31 | even | On delivery
1.04 | Civil and structures | EPC | base | 2726000 | Construction | 2025-07-01 | 2026-04-30 | even | % complete
1.05 | Electrical installation | EPC | base | 2460000 | Construction | 2025-10-01 | 2026-08-31 | even | % complete
1.06 | SCADA and communications | EPC | base | 851000 | SCADA | 2026-02-01 | 2026-09-30 | even | % complete
1.07 | Testing and commissioning | EPC | base | 692000 | Commissioning | 2026-06-01 | 2026-11-30 | even | % complete
1.08 | Early works | Early Works | base | 505000 | Design | 2025-02-01 | 2025-04-30 | even | Monthly
1.09 | Optional: spares package | EPC | optional | 186000 | Procurement | 2026-09-01 | 2026-09-30 | lump | On delivery | confirmed

## Resources
Kind | Code | Name | Function | Work rate code | Cost rate | Sell rate

## Rate card
Department | Role | Work rate code | Cost rate | Sell rate | FY | Rev
PROJECTS | Project Coordinator | PJ03 | 95 | 150 | 26/27 | R00
PROJECTS | Project Engineer | PJ04 | 110 | 200 | 26/27 | R00
PROJECTS | Senior Project Manager | PJ09 | 240 | 283 | 26/27 | R00
DESIGN | Senior Designer | PJ04 | 110 | 240 | 26/27 | R00
COMMISSIONING | Commissioning Engineer | COME | 140 | 210 | 26/27 | R00
SITE | Site Supervisor | PJ05 | 150 | 215 | 26/27 | R00

## Project schedule
Phase | Milestone / activity | Type | Baseline start | Baseline end | Forecast start | Forecast end | PMR row | Actual date
Award | Early works award | Milestone | 2025-02-03 | 2025-02-03 | 2025-02-03 | 2025-02-03
Award | EPC award | Milestone | 2025-05-02 | 2025-05-02 | 2025-05-02 | 2025-05-02
Design | IFC design | Phase | 2025-05-05 | 2025-11-28 | 2025-05-05 | 2025-12-12
Procurement | Main transformer delivery | Milestone | 2026-02-02 | 2026-02-02 | 2026-02-23 | 2026-02-23
Construction | Civil works | Phase | 2025-08-04 | 2026-03-27 | 2025-08-04 | 2026-04-17
Construction | Electrical installation | Phase | 2025-11-03 | 2026-07-31 | 2025-11-03 | 2026-08-28
Commissioning | Energisation | Milestone | 2026-08-31 | 2026-08-31 | 2026-10-30 | 2026-10-30
Completion | Practical completion | Milestone | 2026-10-30 | 2026-10-30 | 2026-11-27 | 2026-11-27

## Read me
Project load template
Fill the blue cells, save, then upload on Setup, Load from Excel. Uploading again updates what is already there.
Project: identity, dates and references. Dates are YYYY-MM-DD.
CBS & Allowance: one row per CBS item below a Pronto category parent (PL01, PS04, ...). Type = Group for an allowance pot (a role or trade from the proposal, no named resource yet); Type = Line for a named employee or company. Group path is optional (use > to nest, for example Civil > Roads).
A Group keeps its own allowance until you transfer it to Lines in the app. Risk left blank takes the project default risk % of the budget.
Method (Lines only): GROUND-UP, CLAIM, BURN-RATE, AT-BUDGET, AT-COMMIT, TOP-DOWN, MANUAL, NONE. Blank takes the default for the category.
Payment Milestones: the proposal price breakdown. Child rows use a dotted Ref (1.01.01 sits under 1.01). Kind is base or optional.
Resources and Rate card are optional. Employees and suppliers are also created automatically from Pronto uploads.
Never type secrets, bank details or individual pay rates into this workbook. Cost rates are by role.

## Lists (hidden)
Parent codes | Parent names | Methods | Type | Kind | Spread
PL01 | Project Mgmt/Admin Labour | GROUND-UP | Group | base | even
PL02 | Design Labour | CLAIM | Line | optional | lump
PL03 | Engineering Labour | BURN-RATE
PL04 | Construction Labour | AT-BUDGET
PL05 | Testing/Compliance Labour | AT-COMMIT
PL06 | Transmission Lines | TOP-DOWN
PL07 | SCADA Labour | MANUAL
PL08 | LAHA | NONE
PS01 | Project Mgmt/Admin Subcontractors
PS02 | Design Subcontractors
PS03 | Engineering Subcontractors
PS04 | Construction Subcontractors
PS05 | Testing/Compliance Subcontractors
PS06 | Transmission Lines
PS07 | SCADA Subcontractors
PM01 | Comms/SCADA Equipment
PM02 | Transformers
PM03 | Primary Equipment
PM04 | Secondary Equipment
PM05 | Cables and Accessories
PM06 | Misc Materials
PM07 | Civil Materials
PM08 | Spares
PE01 | Travel And Accomm
PE02 | Equipment/Plant Hire
PE03 | Site Indirects
PE04 | Vehicle Costs (incl Hire)
PE05 | Freight
PE06 | BG Fees
PE07 | Insurance
PE08 | Misc Overheads
PE09 | Contingency